## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-07-14 | 25702 | RY-LGSP23-10G | (CVE issue) PSGS-2610G_v6.54.3941_Barox: Insecure credential storage (CWE-257 / CWE-522) (SA-2026-019) | 2026/8/10 => 2026/10/7 => 2026/9/15 => 2026/10/31 | 9/3: FW release ETD = Oct 31st. 8/27: FW release ETD = Sep 15th.
2026-07-14 | 25701 | RY-GSP22-26/370 | (CVE issue) PSGS-1528F_v1.03.1724_Barox: When the password reset, an API request GET /user_config?user=<user-id> is triggered, and the response contents of the password field are visually masked in plain text | 2026/10/20 | 9/3: FW release ETD = Oct 20th. 8/6: Clarifying. 7/17: Bug no. 25701.
2026-07-14 | 25700 | RY-LGSP23-10G | (CVE issue) PSGS-2610G_v6.54.3941_Barox: When the password reset, an API request GET /user_config?user=<user-id> is triggered, and the response contents of the password field are visually masked in plain text | 2026/8/10 => 2026/8/31 => 2026/10/7 => 2026/9/15 | 9/3: FW v6.54.4012 was released on Sep 15th. 8/27: FW release ETD = Sep 15th.
2026-06-17 | 25669 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: DHCP server mode repeat to activated and deactivated will make the switch automatically reboot | 2026/7/14 => 2026/8/7 => 2026/8/21 | 8/27: FW v8.90.1931 was released on Aug 21st. 8/20: FW release ETD = Aug 26th if no major issues are found during the re-testing. 8/6: FW release ETD = TBD. 7/23: FW release ETD = Aug 07th. 7/17: Another bug was found during verification; FW release ETD will be updated.
2026-06-17 | 25666 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: When IPv4 DHCP Client Enable is enabled via Web UI > System > IP Address > Settings, the switch fails to send DHCP Discover/Request packets and cannot obtain an IP address from the DHCP server | 2026/7/14 => 2026/8/7 => 2026/8/21 | 8/27: FW v8.90.1931 was released on Aug 21st. 8/20: FW release ETD = Aug 26th. 8/6: Planned to be released with bug no. 25669; ETD = TBD.
2026-07-24 | W2026072302 | All series models | Changes to default config | 2026/8/10 + 2026/8/21 + 2026/10/7 | 8/27: FW v8.90.1931 was released on Aug 21st. 8/20: 38xx series -- planned to be released with bug no. 25669. 26xx series -- planned to be released with bug no. 25700. 8/13: FW v7.10.3224/ VB7.10.3224 and v1.03.1740 were released on Aug 10th.
2026-01-29 | S2026012901 | 38 series models | Barox PSGS-38xx series: LACP Config adjustment_feasibility assessment | Closed | 5/15: Case closed. 3/13: RT provided the evaluation results: In the short term, please follow RT’s recommendation to provide clearer explanations. For the long term, we are evaluating the possibility of unifying the platform in the 2026 version.
2026-05-19 | S2026051901 | 38xx series models | Barox 38xx series models to have the password encrypted (increase the encryption to SHA-512) | 2026/7/14 => 2026/8/7 => 2026/8/21 | 8/27: FW v8.90.1931 was released on Aug 21st. 8/20: FW release ETD = Aug 26th. 8/6: Planned to be released with bug no. 25669; ETD = TBD.
2026-02-03 | S2026020301 | 38xx series models | Barox 38xx series: Linkspeed color unified by software implementation_feasibility assessment | TBD | 5/15: Barox will go with Green for max speed and amber for lower speeds. RT to provide the FW release ETD once confirmed. 3/16: RT provided some comments; waiting for Barox's feedback.
2026-08-29 | 25710 | RY-LGSP23-10G | PSGS-2610G_v6.54.3941_Barox: SNMP trap is not sent when a port goes down | TBD | 9/3: Bug no. 25710; under analysis.
2026-09-01 | S2026090101 | 38xx series models | Barox 38xx series: LLDP-MED support for PoE budget negotiation | 2026/12/15 | 9/3: Feasibility confirmed; ETD = Dec 15th.
Note
text in green = done
text in red = pushed out
text in blue = updated