## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-01-19 | 25467 | IPGS-2710AT_PMB8-001 | IPGS-2710AT_VB7.10.3196_(Barox) ERPS: when creating an ERPS ring with 2pcs IPGS-2710AT and 1pc PSGS-3828XBF, ERPS status and Data forwarding will have issues | TBD
2026-01-19 | 25463 | XFGS-3810A_PMC0-012 | XFGS-3810A_V8.90.1800 Port : (Barox) no SNMP OID to set DDMI configuration | 2026-02-13
2025-12-30 | 25412 | FGS-2628KX(C1)_PMB4-008 | FGS-2628KX_v6.54.3926_Barox: when using snmpwalk to get OID 1.3.6.1.2.1.17.4.3.1.3, around 1000 MAC may have timeout | 2026-02-10
2025-12-29 | 25404 | XFGS-3810A_PMC0-012 | XFGS-3810A v8.90.1800_Barox : DIR of Mapping Configuration at VLAN Translation can not be read/set via SNMP | 2026/1/27 => 2026/2/13
2025-12-11 | 25359 | FGS-2628KX(C1)_PMB4-008 | FGS-2628KX_v6.54.3926_Barox: Using NTP & STP together, The port uptime & STP topology change time( TC last) show inaccurate value | 2026-02-10
2025-12-11 | 25358 | IPGS-2710AT(Rev.Bx)_PMC2-017 | IPGS-2710AT_VB7.10.3196_Barox: When VLAN trunk is configured, performing snmpwalk on the dot1dTpFdbTable OID can lead high CPU usage and SNMP polling timeout | 2026-02-10
2025-12-09 | 25354 | IPGS-2710AT(Rev.Bx)_PMC2-017 | IPGS-2710AT_VB7.10.3196_Barox: Memory leak occurs when running snmpwalk via SNMPv3 | 2026/1/12 => 2026/2/10 | Image is too big.
2025-12-09 | 25353 | IPGS-2710AT(Rev.Bx)_PMC2-017 | IPGS-2710AT_VB7.10.3196_Barox: When several ports are configured as VLAN trunk ports, the CPU usage spikes when they link up and start sending LLDP packets | 2026/1/12 => 2026/2/10 | Image is too big.
2025-12-01 | S2025120201 | 28 and 38 series models | Barox models to have the password encrypted (increase the encryption to SHA-512)_feasibility assessment | TBD | 1/21: a. RT is conducting a feasibility assessment for the 28 and 38 series. b. The current issue is insufficient storage space in the eCos (RY-23xx) series, not the choice of encryption method. Any change to the encryption mechanism would require modifications to the CLI, Web, SNMP, and backend programs, which would in turn lead to storage space constraints. 1/15: The RY-23 series cannot support SHA-256 encryption either due to insufficient memory capacity. Checking if possible to add any kind of encryption for the 23 series. Something better than just simple base64 encoding. 1/8: Due to memory/storage constraints, it is not feasible to implement this requirement [increase the password encryption to SHA-512] on the RY-LGSP23xx series (eCos platform). RT is checking whether it is possible to have SHA-256 encryption in the RY-23series instead.
Note
text in green = done
text in red = pushed out
text in blue = updated