## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-04-09 | 25575 | PSGS-2610G(6KV)_PMB5-008 | PSGS-2610G_v6.54.3930_Barox: Can't delete IP interface via SNMP | TBD | 4/9: Bug no. 25575.
2026-04-02 | 25568 | PSGS-2610G(Rev.Bx)_PMC2-016 | PSGS-2610G_v6.54.3930 (Barox): DMS Link-Local Address binding interface setting and IP address are not kept | 2026/4/28 => TBD | 4/2: Bug no. 25568.
2026-04-02 | 25567 | IPGS-2710AT(Rev.Bx)_PMC2-017 | IPGS-2710AT_VB7.10.3208(Barox): When DMS Link-Local Address binding interface setting is changed, will revert to the VLAN configuration after saving and rebooting | 2026/4/28 => 2026/4/23 | 4/2: Bug no. 25567.
2026-03-09 | 25530 | IPGS-2710AT(Rev.Bx)_ PMC2-017 | IPGS-2710AT_VB7.10.3208_Barox - After upgrading from v7.10.2788 to VB7.10.3208, the switch gets stuck, requires a power cycle, and the PoE FW shows "000-000" | 2026/4/28 => 2026/4/23
2026-02-04 | 25506 | PSGS-2610G_PMB5-008 | PSGS-2610G (RY-LGSP23-10G)_v6.54.3926_Barox: The current MIB file does not support EEE or Green Ethernet related functionalities | 2026/3/17 => 2026/3/30 => TBD | 4/9: Further info -- it has been fixed in version v6.54.3933. However, we have not been able to release it due to another issue found during testing. We will try to get back to you soon with the renewed schedule for the bugfix. 4/1: Another bug found during internal verification.
2026-02-03 | 25503 | IPGS-2712BU_PMB6-006 | IPGS-2712BU_v7.10.3202_Barox: Switch crashes during EAP-TLS authentication process if NAS-Identifier(attribute type 32) is configured | 2026/3/11 => 2026/4/28 => 2026/4/23
2026-01-19 | 25467 (cancelled) | IPGS-2710AT_PMB8-001 | IPGS-2710AT_VB7.10.3196_(Barox) ERPS: when creating an ERPS ring with 2pcs IPGS-2710AT and 1pc PSGS-3828XBF, ERPS status and Data forwarding will have issues | N/A | 2/4: RT provided a configuration method which should be able to solve the issue.
2026-02-03 | S2026020301 | 38 series models | Barox 38 series: Linkspeed color unified by software implementation_feasibility assessment | TBD | 3/16: RT provided some comments; waiting for Barox's feedback.
2026-01-29 | S2026012901 | 38 series models | Barox PSGS-38xx series: LACP Config adjustment_feasibility assessment | TBD | 3/13: RT provided the evaluation results: In the short term, please follow RT’s recommendation to provide clearer explanations. For the long term, we are evaluating the possibility of unifying the platform in the 2026 version.
2025-12-01 | S2025120201 | 28 and 38 series models | Barox models to have the password encrypted (increase the encryption to SHA-512)_feasibility assessment | TBD | 3/12: Using an additional parameter in the username command to differentiate between the legacy and the new encryption methods is technically feasible, and would allow compatibility with both the old and new username password encryption schemes. 1/21: a. RT is conducting a feasibility assessment for the 28 and 38 series. b. The current issue is insufficient storage space in the eCos (RY-23xx) series, not the choice of encryption method. Any change to the encryption mechanism would require modifications to the CLI, Web, SNMP, and backend programs, which would in turn lead to storage space constraints. 1/15: The RY-23 series cannot support SHA-256 encryption either due to insufficient memory capacity. Checking if possible to add any kind of encryption for the 23 series. Something better than just simple base64 encoding. 1/8: Due to memory/storage constraints, it is not feasible to implement this requirement [increase the password encryption to SHA-512] on the RY-LGSP23xx series (eCos platform). RT is checking whether it is possible to have SHA-256 encryption in the RY-23series instead.
Note
text in green = done
text in red = pushed out
text in blue = updated