## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-02-04 | 25506 | PSGS-2610G_PMB5-008 | PSGS-2610G (RY-LGSP23-10G)_v6.54.3926_Barox: The current MIB file does not support EEE or Green Ethernet related functionalities | 2026/3/17 => 2026/3/30 => 2026/5/19 | 5/28: The fix is in FW v6.54.3941 (released on May 19th). 4/9: Further info -- it has been fixed in v6.54.3933. However, we have not been able to release it due to another issue found during testing. We will try to get back to you soon with the renewed schedule for the bugfix. 4/1: Another bug found during internal verification.
2026-01-19 | 25467 (cancelled) | IPGS-2710AT_PMB8-001 | IPGS-2710AT_VB7.10.3196_(Barox) ERPS: when creating an ERPS ring with 2pcs IPGS-2710AT and 1pc PSGS-3828XBF, ERPS status and Data forwarding will have issues | N/A | 2/4: RT provided a configuration method which should be able to solve the issue.
2026-02-03 | S2026020301 | 38xx series models | Barox 38xx series: Linkspeed color unified by software implementation_feasibility assessment | TBD | 5/15: Barox will go with Green for max speed and amber for lower speeds. RT to provide the FW release ETD once confirmed. 3/16: RT provided some comments; waiting for Barox's feedback.
2026-01-29 | S2026012901 | 38 series models | Barox PSGS-38xx series: LACP Config adjustment_feasibility assessment | Closed | 5/15: Case closed. 3/13: RT provided the evaluation results: In the short term, please follow RT’s recommendation to provide clearer explanations. For the long term, we are evaluating the possibility of unifying the platform in the 2026 version.
2026-05-19 | S2026051901 | 38xx series models | Barox 38xx series models to have the password encrypted (increase the encryption to SHA-512) | 2026-07-14 | 5/28: FW release ETD = Jul 14th.
2025-12-01 | S2025120201 | 28xx series models | Barox 28xx series models to have the password encrypted (increase the encryption to SHA-512) | 2026-06-30 | 5/21: FW release ETD = Jun 30th. 5/15: Barox accepts RT's proposal. RT will proceed and provide the FW release ETD once confirmed. 3/12: Using an additional parameter in the username command to differentiate between the legacy and the new encryption methods is technically feasible, and would allow compatibility with both the old and new username password encryption schemes. 1/21: a. RT is conducting a feasibility assessment for the 28 and 38 series. b. The current issue is insufficient storage space in the eCos (RY-23xx) series, not the choice of encryption method. Any change to the encryption mechanism would require modifications to the CLI, Web, SNMP, and backend programs, which would in turn lead to storage space constraints. 1/15: The RY-23 series cannot support SHA-256 encryption either due to insufficient memory capacity. Checking if possible to add any kind of encryption for the 23 series. Something better than just simple base64 encoding. 1/8: Due to memory/storage constraints, it is not feasible to implement this requirement [increase the password encryption to SHA-512] on the RY-LGSP23xx series (eCos platform). RT is checking whether it is possible to have SHA-256 encryption in the RY-23series instead.
Note
text in green = done
text in red = pushed out
text in blue = updated