## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-01-19 | 25467 (cancelled) | IPGS-2710AT_PMB8-001 | IPGS-2710AT_VB7.10.3196_(Barox) ERPS: when creating an ERPS ring with 2pcs IPGS-2710AT and 1pc PSGS-3828XBF, ERPS status and Data forwarding will have issues | N/A | 2/4: RT provided a configuration method which should be able to solve the issue.
2026-07-08 | 25689 | RY-LGSP23-10G | PSGS-2610G_Barox_v6.54.3941: SNMP issue | TBD | 7/8: Bug no. 25689.
2026-06-17 | 25669 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: DHCP server mode repeat to activated and deactivated will make the switch automatically reboot | 2026-07-14 | 6/25: FW release ETD = Jul 14th. 6/17: Bug no. 25669.
2026-06-17 | 25666 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: When IPv4 DHCP Client Enable is enabled via Web UI > System > IP Address > Settings, the switch fails to send DHCP Discover/Request packets and cannot obtain an IP address from the DHCP server | 2026-07-14 | 6/17: Bug no. 25666. FW release ETD = Jul 14th.
2026-02-03 | S2026020301 | 38xx series models | Barox 38xx series: Linkspeed color unified by software implementation_feasibility assessment | TBD | 5/15: Barox will go with Green for max speed and amber for lower speeds. RT to provide the FW release ETD once confirmed. 3/16: RT provided some comments; waiting for Barox's feedback.
2026-01-29 | S2026012901 | 38 series models | Barox PSGS-38xx series: LACP Config adjustment_feasibility assessment | Closed | 5/15: Case closed. 3/13: RT provided the evaluation results: In the short term, please follow RT’s recommendation to provide clearer explanations. For the long term, we are evaluating the possibility of unifying the platform in the 2026 version.
2026-05-19 | S2026051901 | 38xx series models | Barox 38xx series models to have the password encrypted (increase the encryption to SHA-512) | 2026-07-14 | 5/28: FW release ETD = Jul 14th.
Note
text in green = done
text in red = pushed out
text in blue = updated