## Barox tickets
Issue date | Ticket no. | Model Name | Task Name | Status/ETD | Remark
2026-01-19 | 25467 (cancelled) | IPGS-2710AT_PMB8-001 | IPGS-2710AT_VB7.10.3196_(Barox) ERPS: when creating an ERPS ring with 2pcs IPGS-2710AT and 1pc PSGS-3828XBF, ERPS status and Data forwarding will have issues | N/A | 2/4: RT provided a configuration method which should be able to solve the issue.
2026-07-14 | 25703 | RY-GSP22-26/370 | (CVE issue) PSGS-1528F_v1.03.1724_Barox: Insecure credential storage (CWE-257 / CWE-522) (SA-2026-019) | 2026-08-21 | 8/6: FW release ETD = Aug 21st.
2026-07-14 | 25702 | RY-LGSP23-10G | (CVE issue) PSGS-2610G_v6.54.3941_Barox: Insecure credential storage (CWE-257 / CWE-522) (SA-2026-019) | 2026-08-10 | 7/23: FW release ETD = Aug 10th.
2026-07-14 | 25701 | RY-GSP22-26/370 | (CVE issue) PSGS-1528F_v1.03.1724_Barox: When the password reset, an API request GET /user_config?user=<user-id> is triggered, and the response contents of the password field are visually masked in plain text | TBD | 8/6: Clarifying. 7/17: Bug no. 25701.
2026-07-14 | 25700 | RY-LGSP23-10G | (CVE issue) PSGS-2610G_v6.54.3941_Barox: When the password reset, an API request GET /user_config?user=<user-id> is triggered, and the response contents of the password field are visually masked in plain text | 2026/8/10 => 2026/8/31 | 8/6: FW release ETD = Aug 31st.
2026-06-17 | 25669 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: DHCP server mode repeat to activated and deactivated will make the switch automatically reboot | 2026/7/14 => 2026/8/7 => TBD | 8/6: FW release ETD = TBD. 7/23: FW release ETD = Aug 07th. 7/17: Another bug was found during verification; FW release ETD will be updated.
2026-06-17 | 25666 | 38xx series models | XFGS-3810A _ Barox_v8.90.1860 DHCP: When IPv4 DHCP Client Enable is enabled via Web UI > System > IP Address > Settings, the switch fails to send DHCP Discover/Request packets and cannot obtain an IP address from the DHCP server | 2026/7/14 => 2026/8/7 => TBD | 8/6: Planned to be released with bug no. 25669; ETD = TBD.
2026-07-24 | W2026072302 | All series models | Changes to default config | 2026-08-18 | 7/30: FW release ETD = Aug 18th.
2026-07-16 | W2026071601 | RY-GSP22-26/370 | Barox RY-GSP22-26/370 (PSGS-1528F) default config | 2026/8/12 => 2026/8/21 | 8/21: FW release ETD = Aug 21st.
2026-01-29 | S2026012901 | 38 series models | Barox PSGS-38xx series: LACP Config adjustment_feasibility assessment | Closed | 5/15: Case closed. 3/13: RT provided the evaluation results: In the short term, please follow RT’s recommendation to provide clearer explanations. For the long term, we are evaluating the possibility of unifying the platform in the 2026 version.
2026-05-19 | S2026051901 | 38xx series models | Barox 38xx series models to have the password encrypted (increase the encryption to SHA-512) | 2026/7/14 => 2026/8/7 => TBD | 8/6: Planned to be released with bug no. 25669; ETD = TBD.
2026-02-03 | S2026020301 | 38xx series models | Barox 38xx series: Linkspeed color unified by software implementation_feasibility assessment | TBD | 5/15: Barox will go with Green for max speed and amber for lower speeds. RT to provide the FW release ETD once confirmed. 3/16: RT provided some comments; waiting for Barox's feedback.
Note
text in green = done
text in red = pushed out
text in blue = updated